FYP Lifecycle processes 24/25.

Planning Phase

INPUTS:

Idea

Supervisor

ACTIVITIES:

- Interim review. Research question and Research areas.

- Project Plan. Use template below and if necessary, include list software considerations.

| Week | Activities & Estimate | Output | Status | Comments |
| --- | --- | --- | --- | --- |

- Lit Review started and headings identified.

- Risk Analysis.

| Risk Description | Impact (High, med, low) | Likelihood (High, med, low) | Prevention activity | Action plan |
| --- | --- | --- | --- | --- |

OUTPUTS:

Research Question		3/10/24

Research Areas		3/10/24

Project Plan			14/10/24

Risk Analysis			14/10/24

Lit Review write up started. 	14/10/24

Requirements Phase

INPUTS:

Outputs from planning phases (agreed and signed off with supervisor)

ACTIVITIES:

Project specification: Defines the scope, the functional and non-functional

Requirements.

Create a Product Backlog: Prioritised list of epics & some user stories (requirements)

User Story

Unique Number: US 001

Title:

Category: n/a

Owner

Dependency:

Estimate (story points or hours) (not more than 22hrs)

Priority: MoSCow method( Must have, should have, could have, won’t have)

(30:30:30:10)

Description : As a _____ I want ____so that ____.

Acceptance Criteria (Done criteria)

Success

Failure

Test your user stories against the INVEST model

Pick a tool for implementing the Backlog and share with your supervisor

OUTPUTS:

Project specification – Product backlog.

----------------------DONE ----------------------

Design Phase

INPUTS:

Backlog of prioritised epics/user stories

ACTIVITIES:

Design Documents : Should provide the development team with an overview of what to build and how.

Content

Use Cases

*Class Diagrams

System models

Data flow diagrams

*Sequence Diagrams

*Activity Diagrams

*Data Schemas

Story boards

Interface Designs

etc

Tested against Copelands Checklist

Methodologies

Sprint = 2 weeks – 22 hrs  ( 1 week is 5hrs labs + 6hrs)

Activties

Monitoring time spent.

Sprint planning (Decide on items from backlog to implement , agreed with 		supervisor)

Review your user story, acceptance criteria and write your test cases.

Code – Design patterns , framework. Clean code, performance, adhere to language coding standards. Static Analyser.

https://peps.python.org/pep-0008/

Run your tests and review acceptance criteria.

Write up work completed during the sprint.

Demo to your supervisor

Review backlog and make adjustments accordingly.

Reprostictive – compare actual/estimate times.

OUTPUTS:

Design and methodology chapter  18/11/2024

Implementation Phase

INPUTS:

Backlog,

Design doc

Sprint plan

ACTIVITIES:

Implement your sprint plan

OUTPUTS:

5th of December 2024

FYP Document: (Work in progress)

Research Chapters, Methodology & Design Chapter

Some Increments (agreed with supervisor) implemented/tested.

Electronic submissions on Canvas.